## Sheet1
Bug ID | Project Name | Module / Feature | Reported By | Date Reported | Environment | Severity | Priority | Bug Summary / Title | Steps to Reproduce | Expected Result | Actual Result | Status | Assigned To | Attachments / Screenshot | Comments / Notes
BUG001 | ShopEase | Login | Swetha R | 20-Jan-2026 | Chrome 118, Win11 | Critical | High | Login button not working | 1. Go to login page 2. Enter credentials 3. Click login | User should log in | Nothing happens | Open | Dev1 | login_bug.png | Chrome only
BUG002 | ShopEase | Checkout | Swetha R | 20-Jan-2026 | Chrome 118, Win11 | Major | Medium | Coupon code not applied | 1. Add item 2. Apply coupon | Discount applied | No discount | In Progress | Dev2 | coupon_bug.png | Works on Firefox
BUG003 | ShopEase | Search | Swetha R | 21-Jan-2026 | Firefox 115, Win11 | Minor | Low | Search results slow | 1. Enter search term 2. Press enter | Results shown quickly | Delay of 5 sec | Open | Dev3 | search_bug.png | Occurs intermittently
BUG004 | ShopEase | Profile | Swetha R | 21-Jan-2026 | Edge 116, Win11 | Major | High | Profile picture upload fails | 1. Go to profile 2. Upload image | Image uploaded | Error 400 | Open | Dev4 | profile_bug.png | All formats fail
BUG005 | ShopEase | Cart | Swetha R | 22-Jan-2026 | Chrome 118, Win11 | Critical | High | Cart not updating quantity | 1. Add item 2. Change quantity | Quantity updated | Remains same | Open | Dev1 | cart_bug.png | Happens on Chrome
BUG006 | ShopEase | Payment | Swetha R | 22-Jan-2026 | Firefox 115, Win11 | Major | Medium | Payment gateway timeout | 1. Checkout 2. Enter card 3. Pay | Payment successful | Timeout error | In Progress | Dev2 | payment_bug.png | Retry fixes
BUG007 | ShopEase | Login | Swetha R | 23-Jan-2026 | Chrome 118, Win11 | Minor | Low | Forgot password link broken | 1. Click forgot password | Password reset page opens | 404 error | Open | Dev3 | forgot_bug.png | Occurs on mobile
BUG008 | ShopEase | Checkout | Swetha R | 23-Jan-2026 | Edge 116, Win11 | Critical | High | Order confirmation not sent | 1. Place order 2. Check email | Email received | No email | Open | Dev4 | order_bug.png | All orders affected
BUG009 | ShopEase | Wishlist | Swetha R | 24-Jan-2026 | Chrome 118, Win11 | Minor | Low | Wishlist not saving items | 1. Add item to wishlist | Item saved | Not saved | Open | Dev1 | wishlist_bug.png | Works after refresh
BUG010 | ShopEase | Search | Swetha R | 24-Jan-2026 | Firefox 115, Win11 | Major | Medium | Autocomplete suggestion incorrect | 1. Type search term | Correct suggestions | Wrong suggestions | In Progress | Dev2 | autocomplete_bug.png | Random